## Sheet1
FILE: | COT_issues.xls
AUTH: | Weber
RE: | COT Issues discovered during July-2006 Solar-B sims.
HIST: | Drafted 2006-July-10.
NOTES:
RT = "real-time"
ORL = .orl output file = OP/OG file
Generate ramsub id
ID | ISSUE | POSSIBLE ACTION | SIM Step | Comment
1 | COT could not see pointing input file because it had the ".txt" extension. | J-side requests that COT see .txt files. |  |  | Done
2 | The COT expects comments in input files to use "/* foo */" brackets. Sim inputs used "#" prefix. | Edit COT to recognize "#" comments. | Step 4. | For some event files, we deleted the comments, and on others we replaced them with the /* */ style comments. | Done
3 | COT crashed on the sims pointing input file. Believe because blank lines offset the first non-comment line from line #5. | First non-comment line should be 5th line. Investigate why COT crashed and fix. | Between steps 6 and 7. | We never did successfully input the sim pointing file. | Done
4 | The RT command MDP_DUMP_XRTTBL inserted the comment but not the command into the ORL. | Fix this in COT. | Step 15. | We added in the command by hand. | Done
5 | The command MDP_XRT_QT_PROG_SET command gave an invalid (and incorrect) parameter ("34"). | Fix this in COT. | Step 13. | We inputted the correct parameters by hand. | Done
6 | The MDP_XRT_QT_PROG_SET command was issued twice in the sims command plan. The same OG slot ID was used both times, even though the OG definitions were different. | Fix this in COT. | Step 13. | We added in another OG slot definition by hand (number 407) for program 121C. | Done
7 | In the ORL file, "INTERVAL:" was incorrecty written as "INTERVAL". | Fix this in COT. | Step 14. |  | Done
8 | The XRTTBL file has PROG, SEQN, and PARM tags. These were incorrectly closed with ">" instead of "/>". | Fix this in COT. | Step 18. | We corrected these by hand in the XRTTBL file. | Done
9 | The MDP_XRT_QT_PROG_SET and MDP_XRT_FL_PROG_SET commands require a parameter which is hexdec and two-digit. Eg, the COT rendered "05" as "5". | Fix this in COT. | Steps 12 and 13. | We corrected these by hand in orl file. | Done
10 | The COT assigns unique IDs to command and event names. It incorrectly propogated this into the ORL. | Fix this in COT so that the ORL is written this way. | Step 17. | We corrected this by hand during the SIM, but we're now pretty sure that we didn't need to do this, because we think all of these identifiers were located in comments. | Need uniqueness, not changed.
11 | Commands in the sequence definitions in the ORL need to show their parameters. | Fix this in COT. | Step 15. | We actually did not put in the ROI_SET command into the final version of the command plan during the sim -- we instead just implemented it by hand. | Done
12 | XOB events should not automatically include MDP_XRT_CTRL_AUTO. | Fix this in COT. | already fixed prior to sims? |  | Done
13 | Sequences of commands during RT passes should not include OGs or INTERVALS. Only have RT commands or comments. | Fix this in COT. | Step 16. |  | Done
14 | MDP_UPLOAD_XRTTBL is a placeholder instruction to the RT operators (tohbans), and is not a literal command. It should be represented in the ORL as ENTRY: RAM MDP_OBS_X, with the RAMSUB-ID (290-299) as a parameter. See email from Kano (4-July-2006) for an example. | Fix this in COT. | Step 15. |  | Done
15 | COT was missing the commands MDP_XRT_RB_IN and MDP_XRT_RB_OUT. | Fix this in COT. |  |  | Done
16 | The XML table filenames output from the COT should include 4-digit pass IDs. | Fix this in COT. |  |  | After sim
17 | COT should not place NOPs (or any OPs) before OP_START nor after OP_STOP. | Fix this in COT. See Requests list regarding what items to print to the ORL file. | Step 16. |  | Done
18 | The COT lagged after loading in all the input event files. It took ~70 sec to load the stev file, and afterwards there was ~ several second delay on every line selection. (We experimented with loading stev files of various lengths, and the loading time varied with the file length.) | Fix this in COT. | Step 6. | Note: this is probably a problem with any large event file (does not have to be the stev events file). | Progress bar added
19 | An XRTMVB XML table file must be specified, even though it will not actually be used on-board. We may continue to use the dummy file. | Fix this in COT. (Perhaps dummy file should be automatically fixed?) |  |  | Done
20 | "Save Command Plan" doesn't save "Settings…" | Fix this in COT. |  |  | Done
21 | Default tables under "Settings…" should be most recent. | Fix this in COT. |  |  | After sim
22 | Linux version of COT has no Quit function. | Fix this in COT. |  |  | Done
23 | For the COT interface, some text is truncated for the MDP_XRT_QT_PROG_SET command: "servation program". (Shouldn't this field be auto?) | Fix this in COT. |  |  | After sim