## Sheet1
FILE: | COT_requests.xls
AUTH: | Weber
RE: | Requests for COT functionality (or other CO ops functionality) composed during July-2006 Solar-B sims.
HIST: | Drafted 2006-July-10.
NOTES:
RT = "real-time"
ORL = .orl output file = OP/OG file
ID | REQUEST | POSSIBLE ACTION
1 | A way to auto-calculate ROI FOVs given XRT targets and s/c repointings. | Fix this in COT. (?) | After launch
2 | J-side requests that it be made possible to put more than one command per OG. | Fix this in COT. | Available in sim 1
3 | It is not necessary to include every event into the ORL, especially most of the station events. Would still keep radiation belts and CMD_AOS/LOS for RT passes, etc. J-side requests that unnecessary events not be listed in the ORL. | Weber still likes the idea of seeing all events in COT, but J-side might request to suppress that, too. Discuss solutions. | No; waiting for rules list from Science
4 | J-side requests 4 types of password editor access on the COT: simple/table; simple/timeline; advanced/table; advanced/timeline. | We should discuss password and access schemes. Implement in COT. | 6 types supported; available in sim 1
5 | Are we still planning to put all the data rate functionality into the COT (eg, plot, writing output file, etc)? | Fix this in COT. (?) J-side requests that plotting functionality be external to COT. Discuss. | Yes, data rate files, no graph yet
6 | The XML to Hex converter needs to know the choice of RAMSUB-ID for a XRT table upload, because this parameter must appear in the output file. | COT will include RAMSUB-ID parameter in the XRTTBL file as a tag. Matsuzaki will suggest the new tagname. Narukage will fix converter to use this info. | Done
7 | The data rate output file should add a margin to the estimated rate. | Who do we ask about this? Matsuzaki? Can we use a default value for the margin? Will need software functionality somewhere to address this. | Done (see Prefs)
8 | J-side requests that CO not need to enter info which is redundant between the I&Ts and the "Settings…" window, eg, CO identity. Is Plan Start and Stop redundant? | Consider list of possible redundancies. How to address? If not actually redundant, will need to prepare arguments to J-side. | Done
9 | Weber requests to set up a template or checklist for collecting most important planning info from the morning meeting. | Not COT. Maybe software, maybe printout. | n/a
10 | J-side requests COT capability to "reserve" or "save" certain OG IDs for particular recurring functions. | Fix this in COT. Kano requests a conversation with Kent about the dynamic allocation of OG IDs. | After launch
11 | All 50 OG IDs reserved to XRT (400-449) need to be provided in the ORL every day, even if we do not use all of them. This is because the ISACS-PLN software requires the full set in order to properly prepare the differences for upload. | Fix this in COT. | Done
12 | The J-side requests that OG names be descriptive rather than refer to their ID number. | Fix this in COT. I imagine the name can use the info currently written to the corresponding comment line. | Done
13 | J-side requests that SAO explain why the COT combines the table and timeline editors. They do not see any value in this. | Weber volunteers to prepare memo with explanation. Kent and Guth asked to provide info. | n/a
14 | The ORL should not show any OPs during the OP switching period at the end of the first 24 hours of the daily command plan. | Fix this in COT. Matsuzaki has been asked that Chief Planners include START and STOP for these periods in one of the input event files. The COT should recognize this input and ensure no OPs during this period. | After sim
15 | Selecting an XOB causes a duplicate to appear in the XOB menu. We request to not see this. | Discuss as necessary. Fix this in COT if possible. | Done
16 | MDP_XRT_SET_ROI correctly shows parameters. We request to also display values in CCD pixels. | Fix this in COT. | After sim
17 | Weber requests that XOB 1-cycle runtime appear as parenthetical value on XOB, rather than attached to MDP_XRT_CTRL_AUTO. | Let's discuss. | After sim
18 | Request include patrol images in XOB runtime estimates. | Fix this in COT. | Done